## project
Group E -Project Start Date:18th Nov,2016, Target End date: 27th Jan,2016
[7 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Total days | 21
| Man-hour consumed | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY |  | START | DURATION | START | DURATION | COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72
Req. analys. |  | 1 | 21 | 1 | 11 | 100%
Inception | 60 | 1 | 7 | 1 | 7 | 100%
Eleboration | 10 | 8 | 8 | 8 | 4 | 100%
Safety req. |  | 16 | 6 |  |  | 0%
Req. Tr. Matrix |  | 16 | 6 |  |  | 0%
Cocomo Model |  | 7 | 10 | 8 | 14 | 100%
Design |  | 8 | 28 | 8 | 14 | 80%
Implementaion |  | 22 | 28 | 22 | 0 | 25%
Test |  | 36 | 34 |  |  | 0%
Release |  | 69 | 2 |  |  | 0%

## Data
| Start day | Start | End |  | Today | Actual day | Actual day | Progress
total project | 1 | 2016-11-18 | 2017-01-27 | 70 | 2016-12-09 | 21 | 21 |  | Considering Submission
Req. analys. | 1 | 2016-11-18 | 2016-12-09 | 21 | 2016-11-29 | 11 | 11 | 52.381 | Requirement analysis is to be updated If the design team has some feedback or some features which are to be added or deleated
Inception | 1 | 2016-11-18 | 2016-11-25 | 7 | 2016-12-09 | 21 | 21
Eleboration | 8 | 2016-11-25 | 2016-12-03 | 8 | 2016-11-29 | 4 | 4
Safety req. | 16 | 2016-12-03 | 2016-12-09 | 6 | 2016-12-09 | 6 | 6
Req. Tr. Matrix | 16 | 2016-12-03 | 2016-12-09 | 6 | 2016-12-09 | 6 | 6
Cocomo Model | 8 | 2016-11-25 | 2016-12-03 | 8 | 2016-12-09 | 14 | 14
Design | 8 | 2016-11-25 | 2016-12-23 | 28 | 2016-12-09 | 14 | 14
Implementaion | 22 | 2016-12-09 | 2017-01-06 | 28 | 2016-12-09 | 0 | 0
Test | 36 | 2016-12-23 | 2017-01-26 | 34 | 2016-12-09 | -14 | 0
Release | 69 | 2017-01-25 | 2017-01-27 | 2 | 2016-12-09 | -47 | 0

## Timesheet
Team Member
| Total Man Hr. | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
 | time axis 2016-11-18 to 2017-01-27
Member A | 20 | 2016-11-18: 3; 2016-11-21: 2; 2016-11-22: 2; 2016-11-25: 3; 2016-11-28: 2; 2016-11-29: 2; 2016-12-02: 2; 2016-12-06: 2; 2016-12-09: 2
Member B | 20 | 2016-11-18: 3; 2016-11-21: 2; 2016-11-22: 2; 2016-11-25: 3; 2016-11-28: 2; 2016-11-29: 2; 2016-12-02: 2; 2016-12-06: 2; 2016-12-09: 2
Member C | 20 | 2016-11-18: 3; 2016-11-21: 2; 2016-11-22: 2; 2016-11-25: 3; 2016-11-28: 2; 2016-11-29: 2; 2016-12-02: 2; 2016-12-06: 2; 2016-12-09: 2
Member D | 20 | 2016-11-18: 3; 2016-11-21: 2; 2016-11-22: 2; 2016-11-25: 3; 2016-11-28: 2; 2016-11-29: 2; 2016-12-02: 2; 2016-12-06: 2; 2016-12-09: 2
Member E | 20 | 2016-11-18: 3; 2016-11-21: 2; 2016-11-22: 2; 2016-11-25: 3; 2016-11-28: 2; 2016-11-29: 2; 2016-12-02: 2; 2016-12-06: 2; 2016-12-09: 2
Sub Total | 100